## Summary
	Major Work Products	High Level Estimate (Mandays)		Detail Level Estimate (Mandays)		Comments

Pre- / Development	Business requirements Review, Analysis and Estimating (Rat 3)	0.2		10.2
	Functional Requirements (Includes Analysis, Development and Peer Review) (RAT 5, 6 & 9)	0.2		10.2
	Project Management (includes Estimating Time, Paperwork, Other)	0.2		10.2
	Subtotal	0.6		30.6

Development	Development	0.1		5.1
	Scope Classification	0.1		5.1
	Complexity Classification	0.1		5.1
	Risk	0.1		5.1
	Vendor Change	0.1		0.0
	Irac Framework	0.0		0.0
	Etrieve	0.0		0.0
	Herc Required Server Change	0.0		3.0
	Herc Required LDAP Change	3.0		7.7
	Herc Required Database Change	1.8		10.2
	Herc Change to Vendor	2.4		20.9
	Type of Herc change	7.2		0.0
	Architecture/Design	0.0		51.0
	Test Plan and Test Case Development and Peer Review	12.0		0.0
	Developer Testing	30.0		0.0
	Unit Testing	60.0		0.0
	Code Review	20.0		40.0
	Release Notes	40.0		46.0
	RMM Implementation, Support	46.0		15.0
	Subtotal	222.9		214.1

Release	QUAL Implementation, Support	30.0		0.0
	PP Implementation, Support	30.0		0.0
	PROD, Implementation, Support	14.0		0.0
	DM Qual	16.0		0.0
	DM Prod	57.0		0.0
	Subtotal	147.0		0.0

Totals	Size of Work	High Level Estimate (Mandays)		Detailed Estimate (Mandays)
	Pre-Development	2.4		10.2
	Development	12.0		51.0
	Deployment	1.0		1.0
	Totals	15		62

## Jira xxxx
	Work Request Details					Template Version	201
	Jira Number	Jira xxxx		SR xxxx
	Description Name	description					Totals	12	51

	Development Estimates	High Level	Detailed					Requirement/Deliverable	High Level Est	Detail / Est	Comments
		12	51					Change program 1	2	25
				Change program 2	3	12
	Vendor Change	Type	Mandays					Change JSP 1	7	14
	RentalMan	None	0
	AS400	None	0
	Etrieve	None	0
	Rouse	Large	30
	Mindshare	Medium	10
	AirClick	None	0
	SQLServer	None	0
	DB2	None
	Fleet	None	0
	Total		40

	Irac Framework Change	Yes/No	Mandays
	AdminTool	Yes	10
	Database	Yes	5
	Irac Framework	Yes	10
	LDAP	Yes	3
	Properties files	Yes	3
	MapQuest	Yes	10
	Server Change	Yes	5
	Total		46

	Etrieve Change	Yes/No	Mandays
	Etrieve	Yes	2
	RentalManExtracts.jar	Yes	5
	Server Change	Yes	8
	Total		15

	Herc Required Server Change	Yes/No	Mandays
	Datasource	Yes	3
	NSB	Yes	1
	Classpath	Yes	5
	Jars	Yes	10
	Total		19

	Herc Required Firewall Change	Yes/No	Mandays
	Herc Servers	Yes	10
	DM Prod	Yes	10
	DM Qual	Yes	10
	Any other external access	Yes	10
	Total		30

	Herc Required Interwoven Change	Yes/No	Mandays
	General Interwoven change	Yes	10
	Add Interwoven copy script	Yes	10
	Update Interwoven copy script	Yes	10
	Total		30

	Herc Required LDAP Change	Yes/No	Mandays
	New Data Object	Yes	3
	Changed Data Object	Yes	4
	Herc Member Profile	Yes	2
	AdminTool Member Profile	Yes	5
	Total		14

	Herc Required Database Change	Yes/No	Mandays
	Replication	Yes	5
	New Table	Yes	2
	New Index	Yes	1
	Table update	Yes	1
	Table removed	Yes	1
	New Datasource	Yes	1
	Updated Datasource	Yes	1
	Deleted datasource	Yes	1
	Demo data update	Yes	1
	System data update	Yes	1
	Data requires translation	Yes	1
	Total		16

	Herc Change to Vendor	Yes/No	Mandays
	Rouse	Yes	10
	Mindshare	Yes	10
	Fleet	Yes	5
	AS400	Yes	5
	RentalMan	Yes	5
	RentalMan Extracts Jar	Yes	5
	Irac	Yes	10
	Airclick	Yes	5
	Etrieve	Yes	2
	Total		57

	Type of Herc change	Yes/No	Mandays
	New Component	Yes	3
	New Jars	Yes	2
	Updated Jars	Yes	5
	Herc Properties Files	Yes	2
	LDAP api	Yes	2
	DAO Framework Change	Yes	2
	Cache Framework Change	Yes	2
	New Session Objects	Yes	3
	Updated Session Objects	Yes	3
	Total		24

	Functionality	Yes/No
	Reports	Yes
	Email	Yes
	Job Scheduler	Yes
	New Job	Yes
	SEO urls	Yes
	AdminTool	Yes
	Developer only Testing	Yes
	AS400	Yes
	Overdue Rentals	Yes
	Release/Extend	Yes
	Total		0

	Component	Yes/No
	HercAdminToolWeb	No
	HercATCommonUTIL	Yes
	HercFranchiseWeb	No
	HercJobEJB	No
	HercJobSchedulerWeb	No
	HercMindshare	No
	HercMobileWeb	No
	HercPresentationUTIL	No
	HercSalesWeb	No
	HercWeb	No
	HercUTIL	No
	JasperEJB	No
	RentalManEJB	No
	HercRouse	No
	ServicePumpsWeb	No

	Factors	Type	Factor
	Code	New
	Java Refactoring	Yes
	Scope Classification	Medium	30
	Complexity Classification	Large	60
	Risk	Medium	20

	Project Factors	%age	High Level	Detailed
	Functional Requirements (RAT)	15%	1.8	7.65
	Project Management	20%	2.4	10.2
	Architecture/Design	20%	2.4	10.2
	Developer Testing	20%	2.4	10.2
	Unit Testing	100%	12	51
	RMM	20%	2.4	10.2
	Qual	10%	1.2	5.1
	DM Qual	10%	1.2	5.1
	DM Prod	10%	1.2	5.1
	PP	10%	1.2	5.1
	Prod	10%	1.2	5.1

	Major Work Products	High Level Estimate (Mandays)		Detail Level Estimate		Comments

Pre- / Development	Business requirements Review, Analysis and Estimating (Rat 3)	3.0		3.0
	Functional Requirements (Includes Analysis, Development and Peer Review) (RAT 5, 6 & 9)	1.8		7.7
	Project Management (includes Estimating Time, Paperwork, Other)	2.4		10.2
	Subtotal	7.2		20.9

Development	Development	12.0		51.0
	Scope Classification	30
	Complexity Classification	60
	Risk	20
	Vendor Change	40.0		40.0
	Irac Framework	46.0		46.0
	Etrieve	15.0		15.0
	Herc Required Server Change	19.0
	Herc Required Firewall Change	30.0
	Herc Required Interwoven Change	30.0
	Herc Required LDAP Change	14.0
	Herc Required Database Change	16.0
	Herc Change to Vendor	57.0
	Type of Herc change	24
	Architecture/Design	2.4		10.2
	Test Plan and Test Case Development and Peer Review	1.0		1.0
	Developer Testing	2.4		10.2
	Unit Testing	12.0		51.0
	Code Review	1.0		1.0
	Release Notes	1.0		1.0
	RMM Implementation, Support	2		10.2
	Subtotal	435.2		236.6

Release	QUAL Implementation, Support	1.2		5.1
	PP Implementation, Support	1.2		5.1
	PROD, Implementation, Support	1.2		5.1
	DM Qual	1.2		5.1
	DM Prod	1.2		0.5
	Subtotal	6.0		20.9

Totals	Size of Work	High Level Estimate (Mandays)		Detailed Estimate (Mandays)
	Pre-Development	7		21
	Development	435		237
	Deployment	6		21
	Totals	448		278

High Level Estimates	Estimator(s)	Pxxx Mxxx
	Effort Estimate (In Mandays)	448
	Cost Estimate
	Assumption(s)	None
	Date Completed (MM/DD/YYYY)

Detailed Estimates	Estimator(s)	Pxxx Mxxx
	Effort Estimate (In Mandays)	278
	Cost Estimate
	Assumption(s)	None
	Date Completed (MM/DD/YYYY)

Architect	Architect
	Project Risk
	Rollback Estimate
	Date Completed (MM/DD/YYYY)