## Summary
	Major Work Products	High Level Estimate (Mandays)		Detail Level Estimate (Mandays)		Comments

Pre- / Development	Business requirements Review, Analysis and Estimating (Rat 3)	12.0		12.0
	Functional Requirements (Includes Analysis, Development and Peer Review) (RAT 5, 6 & 9)	1.7		0.0
	Project Management (includes Estimating Time, Paperwork, Other)	2.2		0.0
	Subtotal	15.9		12.0

Development	Development	0.0		0.0
	Scope Classification	0.0		0.0
	Complexity Classification	0.0		0.0
	Risk	0.0		40.0
	Vendor Change	40.0		0.0
	Irac Framework	0.0		5.0
	Etrieve	2.0		0.0
	Herc Required Server Change	0.0		0.0
	Herc Required LDAP Change	0.0		0.0
	Herc Required Database Change	0.0		0.0
	Herc Change to Vendor	0.0		0.0
	Type of Herc change	0.0		0.0
	Architecture/Design	1.6		4.0
	Test Plan and Test Case Development and Peer Review	3.0		0.0
	Developer Testing	2.8		0.0
	Unit Testing	8.0		4.0
	Code Review	3.0		4.0
	Release Notes	0.0		0.0
	RMM Implementation, Support	0.4		57.0
	Subtotal	60.8		114.0

Release	QUAL Implementation, Support	1.1		0.0
	PP Implementation, Support	1.1		0.0
	PROD, Implementation, Support	1.1		0.0
	DM Qual	0.2		0.0
	DM Prod	0.2		2.0
	Subtotal	3.7		2.0

Totals	Size of Work	High Level Estimate (Mandays)		Detailed Estimate (Mandays)
	Pre-Development	15.9		12.0
	Development	71.8		57.0
	Deployment	3.7		2.0
	Totals	91		71

## 748
	Work Request Details					Template Version	100
	Jira Number	748		SR49876
	Description Name	N1.1 Homepage Equipment Catalog Search/ R1.8 Rental Catalog Search Result - Need to program to be able to search all contracted items for Logged in Contract members					Totals	6	0

	Development Estimates	High Level	Detailed					Requirement/Deliverable	High Level Est	Detail / Est	Comments
		6	0					Will need to get contract equipments for logged in user. Need to change how the CatalogSearchDataInfo is built.	6
				SearchCatalogHelper is static. It will need to employ the RentalsCatalogHelper pattern.
	Vendor Change	Type	Mandays
	RentalMan	Medium	10					The pattern is to cache the superset of data. Requests to the expert must provide details of the requestor, for example, logged in, userid (to look up any contract items etc).
	AS400	None	0
	Etrieve	None	0
	Rouse	None	0
	Mindshare	None	0
	AirClick	None	0
	SQLServer	None	0
	DB2	None
	Fleet	None	0
	Total		10

	Irac Framework Change	Yes/No	Mandays
	AdminTool	No	0
	Database	No	0
	Irac Framework	No	0
	LDAP	No	0
	Properties files	No	0
	MapQuest	No	0
	Server Change	No	0
	Total		0

	Etrieve Change	Yes/No	Mandays
	Etrieve	No	0
	RentalManExtracts.jar	No	0
	Server Change	No	0
	Total		0

	Herc Required Server Change	Yes/No	Mandays
	Datasource	No	0
	NSB	No	0
	Classpath	No	0
	Jars	No	0
	Total		0

	Herc Required LDAP Change	Yes/No	Mandays
	New Data Object	No	0
	Changed Data Object	No	0
	Herc Member Profile	No	0
	AdminTool Member Profile	No	0
	Total		0

	Herc Required Database Change	Yes/No	Mandays
	Replication	No	0
	New Table	No	0
	New Index	No	0
	Table update	No	0
	Table removed	No	0
	New Datasource	No	0
	Updated Datasource	No	0
	Deleted datasource	No	0
	Demo data update	No	0
	System data update	No	0
	Data requires translation	No	0
	Total		0

	Herc Change to Vendor	Yes/No	Mandays
	Rouse	No	0
	Mindshare	No	0
	Fleet	No	0
	AS400	No	0
	RentalMan	No	0
	RentalMan Extracts Jar	No	0
	Irac	No	0
	Airclick	No	0
	Etrieve	No	0
	Total		0

	Type of Herc change	Yes/No	Mandays
	New Component	No	0
	New Jars	No	0
	Updated Jars	No	0
	Herc Properties Files	No	0
	LDAP api	No	0
	DAO Framework Change	No	0
	Cache Framework Change	No	0
	New Session Objects	No	0
	Updated Session Objects	No	0
	Total		0

	Functionality	Yes/No
	Reports	No
	Email	No
	Job Scheduler	No
	New Job	No
	SEO urls	No
	AdminTool	No
	Developer only Testing	No
	AS400	No
	Overdue Rentals	No
	Release/Extend	No
	Total		0

	Component	Yes/No
	HercAdminToolWeb	No
	HercATCommonUTIL	No
	HercFranchiseWeb	No
	HercJobEJB	No
	HercJobSchedulerWeb	No
	HercMindshare	No
	HercMobileWeb	No
	HercPresentationUTIL	Yes
	HercSalesWeb	No
	HercWeb	Yes
	HercUTIL	Yes
	JasperEJB	No
	RentalManEJB	No
	RouseProject	No
	ServicePumpsWeb	No

	Factors	Type	Factor
	Code	New
	Java Refactoring	Yes
	Scope Classification	Small	0
	Complexity Classification	Small	0
	Risk	Small	0

	Project Factors	%age	High Level	Detailed
	Functional Requirements (RAT)	15%	0.9	0
	Project Management	20%	1.2	0
	Architecture/Design	20%	1.2	0
	Developer Testing	20%	1.2	0
	Unit Testing	100%	6	0
	RMM	20%	1.2	0
	Qual	10%	0.6	0
	DM Qual	10%	0	0
	DM Prod	10%	0	0
	PP	10%	0.6	0
	Prod	10%	0.6	0

	Major Work Products	High Level Estimate (Mandays)		Detail Level Estimate		Comments

Pre- / Development	Business requirements Review, Analysis and Estimating (Rat 3)	3.0		3.0
	Functional Requirements (Includes Analysis, Development and Peer Review) (RAT 5, 6 & 9)	0.9		0.0
	Project Management (includes Estimating Time, Paperwork, Other)	1.2		0.0
	Subtotal	5.1		3.0

Development	Development	6.0		0.0
	Scope Classification	0
	Complexity Classification	0
	Risk	0
	Vendor Change	10.0		10.0
	Irac Framework	0.0		0.0
	Etrieve	0.0		0.0
	Herc Required Server Change	0.0
	Herc Required LDAP Change	0.0
	Herc Required Database Change	0.0
	Herc Change to Vendor	0.0
	Type of Herc change	0
	Architecture/Design	1.0		0.0
	Test Plan and Test Case Development and Peer Review	1.0		1.0
	Developer Testing	1.2		0.0
	Unit Testing	6.0		0.0
	Code Review	1.0		1.0
	Release Notes	0.0		1.0
	RMM Implementation, Support	0		0.0
	Subtotal	26.2		13.0

Release	QUAL Implementation, Support	0.6		0.0
	PP Implementation, Support	0.6		0.0
	PROD, Implementation, Support	0.6		0.0
	DM Qual	0.0		0.0
	DM Prod	0.0		0.5
	Subtotal	1.8		0.5

Totals	Size of Work	High Level Estimate (Mandays)		Detailed Estimate (Mandays)
	Pre-Development	5		3
	Development	26		13
	Deployment	2		1
	Totals	33		17

High Level Estimates	Estimator(s)	PRC1038
	Effort Estimate (In Mandays)	33
	Cost Estimate
	Assumption(s)	None
	Date Completed (MM/DD/YYYY)

Detailed Estimates	Estimator(s)	PRC1038
	Effort Estimate (In Mandays)	17
	Cost Estimate
	Assumption(s)	None
	Date Completed (MM/DD/YYYY)

Architect	Architect
	Project Risk
	Rollback Estimate
	Date Completed (MM/DD/YYYY)

## 1031
	Work Request Details					Template Version	100
	Jira Number	1031		TR xxx
	Description Name	TR: Member 'Default Job Location' POS Not Being Honored Upon Login					Totals	2	0

	Development Estimates	High Level	Detailed					Requirement/Deliverable	High Level Est	Detail / Est	Comments
		2	0					Set the POS when User logged in. Will need to look at LoginHelper.createLoggedInMemberState()	2

	Vendor Change	Type	Mandays
	RentalMan	Large	30
	AS400	None	0
	Etrieve	None	0
	Rouse	None	0
	Mindshare	None	0
	AirClick	None	0
	SQLServer	None	0
	DB2	None
	Fleet	None	0
	Total		30

	Irac Framework Change	Yes/No	Mandays
	AdminTool	No	0
	Database	No	0
	Irac Framework	No	0
	LDAP	No	0
	Properties files	No	0
	MapQuest	No	0
	Server Change	No	0
	Total		0

	Etrieve Change	Yes/No	Mandays
	Etrieve	No	0
	RentalManExtracts.jar	No	0
	Server Change	No	0
	Total		0

	Herc Required Server Change	Yes/No	Mandays
	Datasource	No	0
	NSB	No	0
	Classpath	No	0
	Jars	No	0
	Total		0

	Herc Required LDAP Change	Yes/No	Mandays
	New Data Object	No	0
	Changed Data Object	No	0
	Herc Member Profile	No	0
	AdminTool Member Profile	No	0
	Total		0

	Herc Required Database Change	Yes/No	Mandays
	Replication	No	0
	New Table	No	0
	New Index	No	0
	Table update	No	0
	Table removed	No	0
	New Datasource	No	0
	Updated Datasource	No	0
	Deleted datasource	No	0
	Demo data update	No	0
	System data update	No	0
	Data requires translation	No	0
	Total		0

	Herc Change to Vendor	Yes/No	Mandays
	Rouse	No	0
	Mindshare	No	0
	Fleet	No	0
	AS400	No	0
	RentalMan	No	0
	RentalMan Extracts Jar	No	0
	Irac	No	0
	Airclick	No	0
	Etrieve	No	0
	Total		0

	Type of Herc change	Yes/No	Mandays
	New Component	No	0
	New Jars	No	0
	Updated Jars	No	0
	Herc Properties Files	No	0
	LDAP api	No	0
	DAO Framework Change	No	0
	Cache Framework Change	No	0
	New Session Objects	No	0
	Updated Session Objects	No	0
	Total		0

	Functionality	Yes/No
	Reports	No
	Email	No
	Job Scheduler	No
	New Job	No
	SEO urls	No
	AdminTool	No
	Developer only Testing	No
	AS400	No
	Overdue Rentals	No
	Release/Extend	No
	Total		0

	Component	Yes/No
	HercAdminToolWeb	No
	HercATCommonUTIL	No
	HercFranchiseWeb	No
	HercJobEJB	No
	HercJobSchedulerWeb	No
	HercMindshare	No
	HercMobileWeb	No
	HercPresentationUTIL	Yes
	HercSalesWeb	No
	HercWeb	Yes
	HercUTIL	Yes
	JasperEJB	No
	RentalManEJB	No
	RouseProject	No
	ServicePumpsWeb	No

	Factors	Type	Factor
	Code	New
	Java Refactoring	Yes
	Scope Classification	Small	0
	Complexity Classification	Small	0
	Risk	Small	0

	Project Factors	%age	High Level	Detailed
	Functional Requirements (RAT)	15%	0.3	0
	Project Management	20%	0.4	0
	Architecture/Design	20%	0.4	0
	Developer Testing	20%	0.4	0
	Unit Testing	100%	2	0
	RMM	20%	0.4	0
	Qual	10%	0.2	0
	DM Qual	10%	0	0
	DM Prod	10%	0	0
	PP	10%	0.2	0
	Prod	10%	0.2	0

	Major Work Products	High Level Estimate (Mandays)		Detail Level Estimate		Comments

Pre- / Development	Business requirements Review, Analysis and Estimating (Rat 3)	3.0		3.0
	Functional Requirements (Includes Analysis, Development and Peer Review) (RAT 5, 6 & 9)	0.3		0.0
	Project Management (includes Estimating Time, Paperwork, Other)	0.4		0.0
	Subtotal	3.7		3.0

Development	Development	2.0		0.0
	Scope Classification	0
	Complexity Classification	0
	Risk	0
	Vendor Change	30.0		30.0
	Irac Framework	0.0		0.0
	Etrieve	0.0		0.0
	Herc Required Server Change	0.0
	Herc Required LDAP Change	0.0
	Herc Required Database Change	0.0
	Herc Change to Vendor	0.0
	Type of Herc change	0
	Architecture/Design	0.4		0.0
	Test Plan and Test Case Development and Peer Review	1.0		1.0
	Developer Testing	0.4		0.0
	Unit Testing	2.0		0.0
	Code Review	1.0		1.0
	Release Notes	0.0		1.0
	RMM Implementation, Support	0		0.0
	Subtotal	37.2		33.0

Release	QUAL Implementation, Support	0.2		0.0
	PP Implementation, Support	0.2		0.0
	PROD, Implementation, Support	0.2		0.0
	DM Qual	0.0		0.0
	DM Prod	0.0		0.5
	Subtotal	0.6		0.5

Totals	Size of Work	High Level Estimate (Mandays)		Detailed Estimate (Mandays)
	Pre-Development	4		3
	Development	37		33
	Deployment	1		1
	Totals	42		37

High Level Estimates	Estimator(s)	PRC1038
	Effort Estimate (In Mandays)	42
	Cost Estimate
	Assumption(s)	None
	Date Completed (MM/DD/YYYY)

Detailed Estimates	Estimator(s)	PRC1038
	Effort Estimate (In Mandays)	37
	Cost Estimate
	Assumption(s)	None
	Date Completed (MM/DD/YYYY)

Architect	Architect
	Project Risk
	Rollback Estimate
	Date Completed (MM/DD/YYYY)

## 1054
	Work Request Details					Template Version	100
	Jira Number	1054		SR00000
	Description Name	Add Job Location to the body of the Overdue Email					Totals	2	0

	Development Estimates	High Level	Detailed					Requirement/Deliverable	High Level Est	Detail / Est	Comments
		2	0					Modify the data that is passed to email template	2

	Vendor Change	Type	Mandays
	RentalMan	None	0
	AS400	None	0
	Etrieve	None	0
	Rouse	None	0
	Mindshare	None	0
	AirClick	None	0
	SQLServer	None	0
	DB2	None
	Fleet	None	0
	Total		0

	Irac Framework Change	Yes/No	Mandays
	AdminTool	No	0
	Database	No	0
	Irac Framework	No	0
	LDAP	No	0
	Properties files	No	0
	MapQuest	No	0
	Server Change	No	0
	Total		0

	Etrieve Change	Yes/No	Mandays
	Etrieve	No	0
	RentalManExtracts.jar	Yes	5
	Server Change	No	0
	Total		5

	Herc Required Server Change	Yes/No	Mandays
	Datasource	No	0
	NSB	No	0
	Classpath	No	0
	Jars	No	0
	Total		0

	Herc Required LDAP Change	Yes/No	Mandays
	New Data Object	No	0
	Changed Data Object	No	0
	Herc Member Profile	No	0
	AdminTool Member Profile	No	0
	Total		0

	Herc Required Database Change	Yes/No	Mandays
	Replication	No	0
	New Table	No	0
	New Index	No	0
	Table update	No	0
	Table removed	No	0
	New Datasource	No	0
	Updated Datasource	No	0
	Deleted datasource	No	0
	Demo data update	No	0
	System data update	No	0
	Data requires translation	No	0
	Total		0

	Herc Change to Vendor	Yes/No	Mandays
	Rouse	No	0
	Mindshare	No	0
	Fleet	No	0
	AS400	No	0
	RentalMan	No	0
	RentalMan Extracts Jar	No	0
	Irac	No	0
	Airclick	No	0
	Etrieve	No	0
	Total		0

	Type of Herc change	Yes/No	Mandays
	New Component	No	0
	New Jars	No	0
	Updated Jars	No	0
	Herc Properties Files	No	0
	LDAP api	No	0
	DAO Framework Change	No	0
	Cache Framework Change	No	0
	New Session Objects	No	0
	Updated Session Objects	No	0
	Total		0

	Functionality	Yes/No
	Reports	No
	Email	Yes
	Job Scheduler	Yes
	New Job	No
	SEO urls	No
	AdminTool	No
	Developer only Testing	No
	AS400	No
	Overdue Rentals	Yes
	Release/Extend	No
	Total		0

	Component	Yes/No
	HercAdminToolWeb	No
	HercATCommonUTIL	No
	HercFranchiseWeb	No
	HercJobEJB	Yes
	HercJobSchedulerWeb	No
	HercMindshare	No
	HercMobileWeb	No
	HercPresentationUTIL	No
	HercSalesWeb	No
	HercWeb	No
	HercUTIL	No
	JasperEJB	No
	RentalManEJB	No
	RouseProject	No
	ServicePumpsWeb	No

	Factors	Type	Factor
	Code	New
	Java Refactoring	No
	Scope Classification	Small	0
	Complexity Classification	Small	0
	Risk	Small	0

	Project Factors	%age	High Level	Detailed
	Functional Requirements (RAT)	15%	0.3	0
	Project Management	20%	0.4	0
	Architecture/Design	20%	0.4	0
	Developer Testing	20%	0.4	0
	Unit Testing	100%	2	0
	RMM	20%	0.4	0
	Qual	10%	0.2	0
	DM Qual	10%	0.2	0
	DM Prod	10%	0.2	0
	PP	10%	0.2	0
	Prod	10%	0.2	0

	Major Work Products	High Level Estimate (Mandays)		Detail Level Estimate		Comments

Pre- / Development	Business requirements Review, Analysis and Estimating (Rat 3)	3.0		3.0
	Functional Requirements (Includes Analysis, Development and Peer Review) (RAT 5, 6 & 9)	0.3		0.0
	Project Management (includes Estimating Time, Paperwork, Other)	0.4		0.0
	Subtotal	3.7		3.0

Development	Development	2.0		0.0
	Scope Classification	0
	Complexity Classification	0
	Risk	0
	Vendor Change	0.0		0.0
	Irac Framework	0.0		0.0
	Etrieve	2.0		5.0
	Herc Required Server Change	0.0
	Herc Required LDAP Change	0.0
	Herc Required Database Change	0.0
	Herc Change to Vendor	0.0
	Type of Herc change	0
	Architecture/Design	0.0		0.0
	Test Plan and Test Case Development and Peer Review	1.0		1.0
	Developer Testing	1.0		0.0
	Unit Testing	0.0		0.0
	Code Review	1.0		1.0
	Release Notes	0.0		1.0
	RMM Implementation, Support	0		0.0
	Subtotal	7.0		8.0

Release	QUAL Implementation, Support	0.2		0.0
	PP Implementation, Support	0.2		0.0
	PROD, Implementation, Support	0.2		0.0
	DM Qual	0.2		0.0
	DM Prod	0.2		0.5
	Subtotal	1.0		0.5

Totals	Size of Work	High Level Estimate (Mandays)		Detailed Estimate (Mandays)
	Pre-Development	4		3
	Development	7		8
	Deployment	1		1
	Totals	12		12

High Level Estimates	Estimator(s)	Pxxx Mxxx
	Effort Estimate (In Mandays)	12
	Cost Estimate
	Assumption(s)	None
	Date Completed (MM/DD/YYYY)

Detailed Estimates	Estimator(s)	Pxxx Mxxx
	Effort Estimate (In Mandays)	12
	Cost Estimate
	Assumption(s)	None
	Date Completed (MM/DD/YYYY)

Architect	Architect
	Project Risk
	Rollback Estimate
	Date Completed (MM/DD/YYYY)

## 1064, 1065, 1067
	Work Request Details					Template Version	100
	Jira Number	1064, 1065, 1067		SR xxxx
	Description Name	RTR/RPO Content Updates, US Communities Page Layout and Content Updates, Plant Services Content Update					Totals	1	0

	Development Estimates	High Level	Detailed					Requirement/Deliverable	High Level Est	Detail / Est	Comments
		1	0					No major changes from BE for these three tickets	1

	Vendor Change	Type	Mandays
	RentalMan	None	0
	AS400	None	0
	Etrieve	None	0
	Rouse	None	0
	Mindshare	None	0
	AirClick	None	0
	SQLServer	None	0
	DB2	None
	Fleet	None	0
	Total		0

	Irac Framework Change	Yes/No	Mandays
	AdminTool	No	0
	Database	No	0
	Irac Framework	No	0
	LDAP	No	0
	Properties files	No	0
	MapQuest	No	0
	Server Change	No	0
	Total		0

	Etrieve Change	Yes/No	Mandays
	Etrieve	No	0
	RentalManExtracts.jar	No	0
	Server Change	No	0
	Total		0

	Herc Required Server Change	Yes/No	Mandays
	Datasource	No	0
	NSB	No	0
	Classpath	No	0
	Jars	No	0
	Total		0

	Herc Required LDAP Change	Yes/No	Mandays
	New Data Object	No	0
	Changed Data Object	No	0
	Herc Member Profile	No	0
	AdminTool Member Profile	No	0
	Total		0

	Herc Required Database Change	Yes/No	Mandays
	Replication	No	0
	New Table	No	0
	New Index	No	0
	Table update	No	0
	Table removed	No	0
	New Datasource	No	0
	Updated Datasource	No	0
	Deleted datasource	No	0
	Demo data update	No	0
	System data update	No	0
	Data requires translation	No	0
	Total		0

	Herc Change to Vendor	Yes/No	Mandays
	Rouse	No	0
	Mindshare	No	0
	Fleet	No	0
	AS400	No	0
	RentalMan	No	0
	RentalMan Extracts Jar	No	0
	Irac	No	0
	Airclick	No	0
	Etrieve	No	0
	Total		0

	Type of Herc change	Yes/No	Mandays
	New Component	No	0
	New Jars	No	0
	Updated Jars	No	0
	Herc Properties Files	No	0
	LDAP api	No	0
	DAO Framework Change	No	0
	Cache Framework Change	No	0
	New Session Objects	No	0
	Updated Session Objects	No	0
	Total		0

	Functionality	Yes/No
	Reports	No
	Email	No
	Job Scheduler	No
	New Job	No
	SEO urls	No
	AdminTool	No
	Developer only Testing	No
	AS400	No
	Overdue Rentals	No
	Release/Extend	No
	Total		0

	Component	Yes/No
	HercAdminToolWeb	No
	HercATCommonUTIL	No
	HercFranchiseWeb	No
	HercJobEJB	No
	HercJobSchedulerWeb	No
	HercMindshare	No
	HercMobileWeb	No
	HercPresentationUTIL	No
	HercSalesWeb	No
	HercWeb	No
	HercUTIL	No
	JasperEJB	No
	RentalManEJB	No
	RouseProject	No
	ServicePumpsWeb	No

	Factors	Type	Factor
	Code	New
	Java Refactoring	Yes
	Scope Classification	Small	0
	Complexity Classification	Small	0
	Risk	Small	0

	Project Factors	%age	High Level	Detailed
	Functional Requirements (RAT)	15%	0.15	0
	Project Management	20%	0.2	0
	Architecture/Design	20%	0.2	0
	Developer Testing	20%	0.2	0
	Unit Testing	100%	1	0
	RMM	20%	0.2	0
	Qual	10%	0.1	0
	DM Qual	10%	0	0
	DM Prod	10%	0	0
	PP	10%	0.1	0
	Prod	10%	0.1	0

	Major Work Products	High Level Estimate (Mandays)		Detail Level Estimate		Comments

Pre- / Development	Business requirements Review, Analysis and Estimating (Rat 3)	3.0		3.0
	Functional Requirements (Includes Analysis, Development and Peer Review) (RAT 5, 6 & 9)	0.2		0.0
	Project Management (includes Estimating Time, Paperwork, Other)	0.2		0.0
	Subtotal	3.4		3.0

Development	Development	1.0		0.0
	Scope Classification	0
	Complexity Classification	0
	Risk	0
	Vendor Change	0.0		0.0
	Irac Framework	0.0		0.0
	Etrieve	0.0		0.0
	Herc Required Server Change	0.0
	Herc Required LDAP Change	0.0
	Herc Required Database Change	0.0
	Herc Change to Vendor	0.0
	Type of Herc change	0
	Architecture/Design	0.2		0.0
	Test Plan and Test Case Development and Peer Review	0.0		1.0
	Developer Testing	0.2		0.0
	Unit Testing	0.0		0.0
	Code Review	0.0		1.0
	Release Notes	0.0		1.0
	RMM Implementation, Support	0		0.0
	Subtotal	1.4		3.0

Release	QUAL Implementation, Support	0.1		0.0
	PP Implementation, Support	0.1		0.0
	PROD, Implementation, Support	0.1		0.0
	DM Qual	0.0		0.0
	DM Prod	0.0		0.5
	Subtotal	0.3		0.5

Totals	Size of Work	High Level Estimate (Mandays)		Detailed Estimate (Mandays)
	Pre-Development	3		3
	Development	1		3
	Deployment	0		1
	Totals	5		7

High Level Estimates	Estimator(s)	Pxxx Mxxx
	Effort Estimate (In Mandays)	5
	Cost Estimate
	Assumption(s)	None
	Date Completed (MM/DD/YYYY)

Detailed Estimates	Estimator(s)	Pxxx Mxxx
	Effort Estimate (In Mandays)	7
	Cost Estimate
	Assumption(s)	None
	Date Completed (MM/DD/YYYY)

Architect	Architect
	Project Risk
	Rollback Estimate
	Date Completed (MM/DD/YYYY)